## overview
| ODP Data Migration Projects - Overview | May 2008
Project | Data Type | Status % Complete | Start - End Dates
A | Core, Sample | 100% | Jan-97 - Aug-98
B | MST - GRAPE, P-Wave, Magnetic susceptibility, Natural gamma, and Color Reflectance | 100% | Sep-98 - Aug-01
C | Physical Properties - Thermal conductivity, Moisture & Density, PWS, Shear strength | 100% | Dec-99 - Aug-02
D | Chemical Properties - Rock Eval, Carbonates, Interstitial water, Gases, XRF, XRD | 100% | Apr-01 - Jun-04
E | Miscellaneous - Paleomag, Downhole temperature, Splicer | 100% | Mar-02 - June-03
F | Paleontology - Paleo sample information, Range chart, Age model | 100% | Dec-01 - May-08
G1 | ODP Core Photo Scan | 100% | Dec-01 - May-06
G2 | Visual Core Description Scan | 100% | Mar-03 - Sep-06
G3 | ODP Close-up Photo Scan | 100% | Jun-06 - Feb-08
G4 | DSDP Core Photo Scan | 100% | Jun-06 - Sep-07
We gratefully acknowledge the financial support from NSF.

## mst
MST and Color Reflectance Data Migration
| Start Date: September 1998 | [8 empty] | COMPLETED | [6 empty] | Completion Date: August 2001
Leg / Data | 170 | 169 | 168 | 167 | 166 | 165 | 164 | 163 | 162 | 161 | 160 | 159 | 158 | 157 | 156 | 155 | 154 | 153 | 152 | 151 | 150 | 149 | 148 | 147 | 146 | 145
GRAPE | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | o | x | x | x
P-Wave | x | x | x | x | x | x | x | o | x | x | x | x | x | x | x | x | x | o | x | x | x | x | o | x | x | x
MagSus | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | o | x | x | x
NGR | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | o | x | x | x | 1
Color Reflectance | x | x | x | o | x | x | x | o | o | x | x | x | o | x | x | o | x | 2
Leg / Data | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 137 | 136 | 135 | 134 | 133 | 132 | 131 | 130 | 129 | 128 | 127 | 126 | 125 | 124 | 123 | 122 | 121 | 120 | 119
GRAPE | x | x | o | x | o | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
P-Wave | x | x | o | x | o | x | x | o | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
MagSus | x | x | o | x | o | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
NGR
Color Reflectance
Leg / Data | 118 | 117 | 116 | 115 | 114 | 113 | 112 | 111 | 110 | 109 | 108 | 107 | 106 | 105 | 104 | 103 | 102 | 101 |  | Legend:
GRAPE | o | x | x | x | x | x | x | x | x | o | x | x | o | x | x | x | o | x |  | x | Migration to Janus database completed
P-Wave | o | x | x | x | x | x | x | o | x | o | x | o | o | o | o | o | o | o |  | o | Data not acquired by ODP
MagSus | x | x | x | x | x | o | o | x | x | o | o | x | x | x | x | o | o | o |  | 1 | NGR acquisition started Leg 150
NGR | [17 empty] | 1 |  | 2 | Reflectance acquisition started Leg 154
Color Reflectance | [17 empty] | 2 |  |  | Magsus Leg 104-130 in S1032
[17 empty] | Completed = 210 |  |  |  | = | 100 | %
[17 empty] | Remaining = 0 | [7 empty] | Oct. 3, 2001

## physprops
Physical Properties Data Migration
| Start Date: December 1999 | [8 empty] | COMPLETED | [6 empty] | Completion Date: August 2002
Leg / Data | 170 | 169 | 168 | 167 | 166 | 165 | 164 | 163 | 162 | 161 | 160 | 159 | 158 | 157 | 156 | 155 | 154 | 153 | 152 | 151 | 150 | 149 | 148 | 147 | 146 | 145
Thermcon | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
MAD | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
PWS | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | o | o | x | x | x
Shear Strength | x | o | x | o | x | x | x | o | x | o | x | x | o | x | x | x | x | o | x | x | o | x | o | o | x | x
Leg / Data | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 137 | 136 | 135 | 134 | 133 | 132 | 131 | 130 | 129 | 128 | 127 | 126 | 125 | 124 | 123 | 122 | 121 | 120 | 119
Thermcon | x | x | o | x | x | o | x | o | x | x | x | o | o | x | x | x | x | x | x | x | x | x | x | x | x | x
MAD | x | o | o | x | o | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
PWS | x | o | o | x | o | x | x | x | x | x | x | x | x | x | o | x | x | x | x | x | x | x | x | x | x | x
Shear Strength | x | o | o | o | o | o | x | o | x | x | x | x | x | x | o | x | x | o | x | x | x | x | x | x | x | x
Leg / Data | 118 | 117 | 116 | 115 | 114 | 113 | 112 | 111 | 110 | 109 | 108 | 107 | 106 | 105 | 104 | 103 | 102 | 101 |  | Legend:
Thermcon | x | x | x | x | x | x | x | x | x | x | x | x | o | x | x | x | o | x |  | x | Migration to Janus database completed
MAD | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | o | x |  | o | Data not acquired by ODP
PWS | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | o | x
Shear Strength | o | x | x | x | x | x | x | x | x | o | x | x | o | x | x | x | o | x
[16 empty] | Completed = 241 |  |  |  | = | 100 | %
Remaining = 0
2002-09-23

## chem
Chemistry Data Migration
| Start Date: April 2001 | [8 empty] | COMPLETED | [6 empty] | Completion Date: June 2004
Leg / Data | 170 | 169 | 168 | 167 | 166 | 165 | 164 | 163 | 162 | 161 | 160 | 159 | 158 | 157 | 156 | 155 | 154 | 153 | 152 | 151 | 150 | 149 | 148 | 147 | 146 | 145
Rock Eval | x | o | x | x | x | x | x | o | x | x | x | x | o | x | x | x | o | o | x | x | x | x | o | o | o | o
Carbonates | x | x | x | x | x | x | x | o | x | x | x | x | x | x | x | x | x | o | x | x | x | x | x | x | x | x
Interstitial Water | x | x | x | x | x | x | x | o | x | x | x | x | x | x | x | x | x | o | x | x | x | x | o | o | x | x
Gases | x | x | x | x | x | x | x | o | x | x | x | x | o | x | x | x | x | o | x | x | x | x | o | o | x | x
XRF | o | x | x | o | x | x | o | x | o | x | o | o | x | x | o | x | o | x | x | x | x | x | x | x | o | x
XRD | x | x | x | x | x | x | x | x | x | x | x | x | o | x | x | x | x | x | x | x | x | x | o | x | x | o
Leg / Data | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 137 | 136 | 135 | 134 | 133 | 132 | 131 | 130 | 129 | 128 | 127 | 126 | 125 | 124 | 123 | 122 | 121 | 120 | 119
Rock Eval | x | x | o | x | o | o | o | o | o | x | o | x | o | o | x | o | x | x | o | o | x | x | x | x | x | x
Carbonates | x | x | o | x | o | x | x | o | o | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Interstitial Water | x | x | o | x | o | x | x | o | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Gases | x | x | o | x | o | o | x | o | x | x | x | x | x | o | x | x | x | x | x | x | x | x | x | x | x | x
XRF | x | x | x | x | x | x | x | x | x | x | x | o | o | o | x | o | x | x | x | x | x | x | o | x | x | x
XRD | x | o | o | o | o | o | x | o | x | x | x | x | o | o | x | x | x | x | x | x | x | x | x | x | x | x
Leg / Data | 118 | 117 | 116 | 115 | 114 | 113 | 112 | 111 | 110 | 109 | 108 | 107 | 106 | 105 | 104 | 103 | 102 | 101
Rock Eval | o | x | x | o | x | x | x | x | x | o | x | o | o | x | x | x | o | x
Carbonates | x | x | x | x | x | x | x | x | x | o | x | x | o | x | x | x | o | x
Interstitial Water | o | x | x | x | x | x | x | x | x | o | x | x | o | x | x | x | o | x
Gases | o | x | x | x | x | x | x | o | x | o | x | x | o | x | x | o | o | x
XRF | x | o | x | x | x | x | o | x | o | x | o | o | x | o | o | o | o | o
XRD | x | x | o | x | x | x | x | x | x | x | x | o | x | o | o | o | o | o
Legend:
x | Migration to Janus database completed.
o | Data not acquired by ODP
| Data scanned from microfilms and made available in pdf format | [23 empty] | 2004-06-25

## misc
Miscellaneous Data Migration
| Start Date: March 2002 | [8 empty] | COMPLETED | [6 empty] | Completion Date: June 2003
Leg / Data | 170 | 169 | 168 | 167 | 166 | 165 | 164 | 163 | 162 | 161 | 160 | 159 | 158 | 157 | 156 | 155 | 154 | 153 | 152 | 151 | 150 | 149 | 148 | 147 | 146 | 145
Paleomag | x | x | x | x | x | x | o | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | o | x | x | x
Downhole temp | x | x | x | x | x | o | o | o | x | x | x | x | o | x | x | x | x | o | x | x | x | x | o | o | x | x
Splicer | o | o | o | x | o | o | o | o | x | x | x | o | o | o | o | o | x | o | o | o | o | o | o | o | o | o
Leg / Data | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 137 | 136 | 135 | 134 | 133 | 132 | 131 | 130 | 129 | 128 | 127 | 126 | 125 | 124 | 123 | 122 | 121 | 120 | 119
Paleomag | x | x | o | x | o | x | x | o | x | x | x | x | o | x | x | x | x | x | x | x | x | x | x | x | x | x
Downhole temp | o | o | o | x | o | x | o | o | o | x | x | o | o | x | o | o | x | x | x | x | o | o | x | x | x | x
Splicer | o | o | o | o | o | o | x | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o
Leg / Data | 118 | 117 | 116 | 115 | 114 | 113 | 112 | 111 | 110 | 109 | 108 | 107 | 106 | 105 | 104 | 103 | 102 | 101
Paleomag | x | x | x | x | x | o | o | o | o | o | x | x | o | x | x | x | o | o
Downhole temp | o | x | x | x | o | x | x | x | x | o | o | x | o | x | x | o | o | o
Splicer | o | x | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o
Legend: | x | Migration to Janus database completed
| o | Data not acquired by ODP
2004-06-25

## paleontology
Paleontology Data Migration
| Start Date: December 2001 | [8 empty] | COMPLETED | [6 empty] | Target Completion Date: Sept. 2007
Leg / Data | 170 | 169 | 168 | 167 | 166 | 165 | 164 | 163 | 162 | 161 | 160 | 159 | 158 | 157 | 156 | 155 | 154 | 153 | 152 | 151 | 150 | 149 | 148 | 147 | 146 | 145
Sample investigation | x | x | x | x | x | x | x | o | x | x | x | x | o | x | x | x | x | o | x | x | x | x | o | o | x | x
Range charts | x | x | x | x | x | x | x | o | x | x | x | x | o | x | x | x | x | o | x | x | x | x | o | o | x | x
Age model | x | o | x | o | x | x | o | o | x | x | x | x | o | x | o | o | x | o | o | o | x | x | o | o | o | x
Leg / Data | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 137 | 136 | 135 | 134 | 133 | 132 | 131 | 130 | 129 | 128 | 127 | 126 | 125 | 124 | 123 | 122 | 121 | 120 | 119
Sample investigation | x | x | o | x | o | x | x | o | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Range charts | x | x | o | x | o | x | x | o | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Age model | x | o | o | o | o | o | o | o | o | x | o | x | o | x | x | o | x | x | x | x | x | o | o | x | x | x
Leg / Data | 118 | 117 | 116 | 115 | 114 | 113 | 112 | 111 | 110 | 109 | 108 | 107 | 106 | 105 | 104 | 103 | 102 | 101
Sample investigation | o | o | x | x | x | x | x | x | x | o | x | x | o | x | x | x | o | x
Range charts | o | o | x | x | x | x | x | x | x | o | x | x | o | x | x | x | o | x
Age model | o | x | x | x | x | x | o | x | o | o | x | o | o | x | x | o | o | x
Legend: | x | Migration to Janus database completed | [15 empty] | Completed 58 Legs = |  |  |  |  | 100 | %
| o | Data not acquired by ODP | [15 empty] | All IR and SR tables completed
Not Collected on 12 Legs
2008-05-30

## Photo
Core Photo & Visual Core Description
| Start Date: December 2001 | [8 empty] | COMPLETED | [6 empty] | Target Completion Date: Dec. 2007
Leg / Data | 210 | 209 | 208 | 207 | 206 | 205 | 204 | 203 | 202 | 201 | 200 | 199 | 198 | 197 | 196 | 195 | 194 | 193 | 192 | 191 | 190 | 189 | 188 | 187 | 186 | 185
ODP Core Photo Scan | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Visual Core Description Scan | x | o | x | x | x | x | x | x | x | x | x | x | x | x | o | x | x | x | x | x | x | x | x | o | x | x
ODP Close-up Photo Scan | x | x | x | x | x | x | x | x | x | x | x | x | x | x | o | x | x | x | x | x | x | x | x | x | x | x
DSDP Core Photo Scan * | 1 | [13 empty] | x | x | x | x | x | x | x | x | x | x | x | x
Leg / Data | 184 | 183 | 182 | 181 | 180 | 179 | 178 | 177 | 176 | 175 | 174 | 173 | 172 | 171 | 170 | 169 | 168 | 167 | 166 | 165 | 164 | 163 | 162 | 161 | 160 | 159
ODP Core Photo Scan | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Visual Core Description Scan | o | x | x | x | x | o | x | o | o | o | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
ODP Close-up Photo Scan | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
DSDP Core Photo Scan * | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Leg / Data | 158 | 157 | 156 | 155 | 154 | 153 | 152 | 151 | 150 | 149 | 148 | 147 | 146 | 145 | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 137 | 136 | 135 | 134 | 133
ODP Core Photo Scan | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Visual Core Description Scan | o | x | x | x | x | o | x | x | x | x | o | x | x | x | x | x | o | x | o | x | o | o | x | x | x | x
ODP Close-up Photo Scan | x | x | x | x | x | x | x | x | x | x | o | x | x | x | x | x | x | x | x | x | x | o | x | x | x | x
DSDP Core Photo Scan * | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Leg / Data | 132 | 131 | 130 | 129 | 128 | 127 | 126 | 125 | 124 | 123 | 122 | 121 | 120 | 119 | 118 | 117 | 116 | 115 | 114 | 113 | 112 | 111 | 110 | 109 | 108 | 107
ODP Core Photo Scan | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Visual Core Description Scan | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
ODP Close-up Photo Scan | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
DSDP Core Photo Scan * | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Leg / Data | 106 | 105 | 104 | 103 | 102 | 101 |  | Completed
ODP Core Photo Scan | x | x | x | x | o | x |  | 100 | % |  |  | Legend: | x | Migration to Janus database completed
Visual Core Description Scan | x | x | x | x | o | x |  | 100 | % |  |  |  | o | Data not acquired by ODP
ODP Close-up Photo Scan | o | x | x | x | o | x |  | 100 | % |  |  |  | * | Actual DSDP Leg = Reported Leg - 100
DSDP Core Photo Scan * | x | x | x | x | x | x |  | 100 | % |  |  |  | 1 | DSDP ended at the end of Leg 96 | [9 empty] | 2008-02-11